## TOURiBBOSTER_TIMETABLE
TOURIBOOSTER
CfP 2018/KA2/StrategicPartnerships/HE
| Reorienting tourism education with digital, social and intercultural competences to support local stakeholders tackle strategic innovation in tourism | [7 empty] | 2018 (CALENDAR YEAR 1) |  |  |  | 2019 (CALENDAR YEAR 2) | [11 empty] | 2020 (CALENDAR YEAR 3)
[9 empty] | 1st SEMESTER |  |  |  | 2nd SEMESTER | [5 empty] | 3rd SEMESTER
OUTPUTS | ACTIVITIES | QUANTIFIED OUTPUTS | Measurement Unit | Target Value | QUANTIFIED RESULTS | Measurement Unit | Target Value | LEAD | SEPTEMBER (M1) | OCTOBER (M2) | NOVEMBER (M3) | DECEMBER (M4) | JANUARY (M5) | FEBRUARY (M6) | MARCH (M7) | APRIL (M8) | MAY (M9) | JUNE (M10) | JULY (M11) | AUGUST (M12) | SEPTEMBER (M13) | OCTOBER (M14) | NOVEMBER (M15) | DECEMBER (M16) | JANUARY (M17) | FEBRUARY (M18) | MARCH (M19) | APRIL (M20) | MAY (M21) | JUNE (M22) | JULY (M24 | AUGUST (M24)
TRANSNATIONAL PROJECT MANAGEMENT, ADMINISTRATION, COORDINATION & MONITORING | 1.1: TRANSNATIONAL PROJECT MANAGEMENT AND ADMINISTRATION | • Contractual Procedure | • No of official docs signed (Grant Agreement, Consortium Agreement) | • 2 | • New Transnational Partnership established | • No of Project Partners activated | • 6 | PC (NEU) | ·
|  | • Steering Group Committee, Technical Committee, Quality Control Committee | • No of Project Committees established (SGC, TC, QCC) | • 3 | • Common Management Structure established | • No of Common Management Structure adopted | • 1 | PC (NEU) |  |  |  | ●
|  | • The Project Management Toolkit | • No of common management tools developed | • 4 | • Common Management Standards adopted | • No of Common Management Standards adopted | • 4 | PC (NEU) |  | « | · | « | « | « | « | « | « | « | · | « | « | « | « | « | · | « | « | « | « | « |  | ·
|  | • The Quality Assurance Plan | • No of common management tools developed | • 5 | • Common Management Standards adopted | • No of Common Management Standards adopted | • 5 | PP3 (KJF) |  |  | ·
|  | • Compilation of the Project’s AV and Media Record | • No of docs and media formats compiled | • 300 | • Stakeholders with direct access to the Project Record | • No of Stakeholders with direct access to the Project Record | • 160 (60 SMEs and 100 Stakeholders) | PC (NEU) |  | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | ·
| 1.2: TRANSNATIONAL PROJECT COORDINATION | • no of project coordination meetings implemented | · no of project coordination meetings implemented | · 6 (4 physical and 2 teleconferences) | · Staff members with increased capacities in the management of EU Projects developed | • No of Staff members with increased capacities in the management of EU Projects developed | • 30(5*6) | PC |  | « | « | · |  |  |  |  | · |  |  |  | ● |  |  | ● |  |  | · |  |  | ●
| 1.3 TRANSNATIONAL PROJECT MONITORING | • Organizational Chart • Project Checklists for the Quality of Project Deliverables • Internal Interim Reports | • Organizational Chart • Project Checklists for the Quality of Project Deliverables • Internal Interim Reports | • 1 • 1 • 4 | • Physical object implemented • Project budget absorbed • Project Completion Statement | • % of the physical object implemented • % of Project Budget absorbed • no of Project Completion Statements | • 95% of the physical project object implemented • 95% of the financial project object implemented • 1 | PC | « | « | « | « | ● | « | « | « | « | ● | « | « |  | « | « | « | ● | « | « | « | « | « | « | ●
|  | • Interim Report • Final Report | • no of interim reports • no of final reports | • 1 • 1 | • Physical object implemented • Project budget absorbed • Project Completion Statement | • % of the physical object implemented • % of Project Budget absorbed • no of Project Completion Statements | • 95% of the physical project object implemented • 95% of the financial project object implemented • 1 | PC | « | « | « | « | ● | « | « | « | « | ● | « | « | £ | « | « | « | ● | « | « | « | « | « | « | ● | « | « | £
COMMUNICATION, DISSEMINATION AND VISIBILITY | ACTIVITIES | QUANTIFIED OUTPUTS | Measurement Unit | Target Value | QUANTIFIED RESULTS | Measurement Unit | Target Value | LEAD | SEPTEMBER (M1) | OCTOBER (M2) | NOVEMBER (M3) | DECEMBER (M4) | JANUARY (M5) | FEBRUARY (M6) | MARCH (M7) | APRIL (M8) | MAY (M9) | JUNE (M10) | JULY (M11) | AUGUST (M12) | SEPTEMBER (M13) | OCTOBER (M14) | NOVEMBER (M15) | DECEMBER (M15) | JANUARY (M17) | FEBRUARY (M18) | MARCH (M19) | APRIL (M20) | MAY (M21) | JUNE (M22) | JULY (M24 | AUGUST (M24)
| 2.1 : THE PROJECT’s INTEGRATED COMMUNICATION, DISSEMINATION, VISIBILITY AND TRANSPARENCY SOURCES | • The Project’s Integrated Communication, Dissemination and Visibility Platform | • no of highly advanced ICT tools utilized | • 2 (website and Moodle Platform) | • Permanent Information and Transparency Sources for Project Activities | • No of Permanent Information and Transparency Sources for Project Activities | • 2 | PC (NEU) | · | « | · | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | ·
|  | • The TOURiBOOSTER Social Media Campaign | • no of social media tools utilized | • 4 (Instagram, Pinterest, Facebook Metrics, Twitter) | • Development of social media communities for the DIVERTIMENTO heritage game | • No of social media communities involved in the heritage game | • 14 (2*7) | PP2 (TÜRSAB) |  | · | · | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | ·
| 2.2. PROJECT-DRIVEN COMMUNICATION STRATEGY FOR SELECTED TARGET PUBLICS FROM THE PUBLIC, PRIVATE AND THIRD SECTOR AT EU AND INTERNATIONAL LEVEL | • The Common Visibility, Communication and Dissemination Plan (CDV Plan) PC | • No of CDV Plans developed | • 1 | • Innovative communication concept implemented | • no of innovative communication concepts implemented | • 1 | PC: PP6 (ARTIFACTORY); «: ·
|  | • Press Conferences | • No of Press Conferences | • 2 (Kick Off Meeting & Multiplier Event) | • Press articles published about Project activities in the Cooperation Area | • no of press articles published about Project activities in the Cooperation Area | 8 | PC: PC (NEU) & PP2 (TÜRSAB); «: ·; «: «; «: «; «: ·; «: ●
| 2.3 DISSEMINATION OF PROJECT OUTPUTS & PROJECT BRANDING AT INTERNATIONAL LEVEL | • The TOURiBOOST Visual Identity Kit (Project Logo; Stand with Banner; Mousepad Calendar; Pen; Cotton Bag ) | • No of brochures | • 1 | • Tourism stakeholders directly reached in the project area | • No of tourism stakeholders directly reached in the Cooperation Area | • 140 (20*7) | PC: PC (NEU); «: ·
|  | • Project Brochure | • No of visual identity tools produced | • 15 | • Joint Outreach Tools to reach directly Tourism stakeholders in the project area | • No of Joint Outreach Tools to reach directly Tourism stakeholders in the project area | • 1 | PC: PC (NEU); «: ·
|  | • 6 Project Newsletters | • No of Newsletters |  | • Joint Outreach Tools to reach directly Tourism stakeholders in the project area | • No of Joint Outreach Tools to reach directly Tourism stakeholders in the project area | • 6 | PC: PP2 (TÜRSAB); «: ·; ●: ●
|  | • The TOURIBBOSTER Promotional Spot | • No of AV productions implemented | • 1 | • Heritage tourism products proactively promoted | • No of heritage products proactively promoted | • 7 | PP2 (TÜRSAB) |  |  |  |  | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | « | «
[9 empty] | SEPTEMBER (M1) | OCTOBER (M2) | NOVEMBER (M3) | DECEMBER (M4) | JANUARY (M5) | FEBRUARY (M6) | MARCH (M7) | APRIL (M8) | MAY (M9) | JUNE (M10) | JULY (M11) | AUGUST (M12) | SEPTEMBER (M13) | OCTOBER (M14) | NOVEMBER (M15) | DECEMBER (M15) | JANUARY (M17) | FEBRUARY (M18) | MARCH (M19) | APRIL (M20) | MAY (M21) | JUNE (M22) | JULY (M24 | AUGUST (M24)
IO1 | IDENTIFICATION OF SKILLS NEEDS AND EMERGING SKILLS TO ASSIST CAPACITY BUILDING OF TOURISM STAKEHOLDERS | • Joint Survey Study to Investigate Entrepreneurial/Stakeholders Needs and Skill Needs of Human Capital in the Project Area | • No of joint surveys conducted | • 1 | • Recommendations for the skills updates | • No of recommendations for the skills updates | • 12 | PC: P3 (KJF); ●: «; «: «; «: ●; «: ●
|  | • Stakeholder Training Workshops to identify a new generation of experience-based tourism products in the territory | • No of Stakeholder Workshops | • 1 | • New products and services detected | • No of new products and services detected | • 1 | PC: ALL; ●: ·
|  | • Research Report | • No of Research Reports | • 1 | • New business models detected | • No of new business models detected | • 6 | PC: ALL; £: ●
IO2 | LINKING STAKEHOLDER EDUCATION TO KEY TOURISM EXPERIENCES AND QUALITY SERVICES IN THE TERRITORY | ● Massive Online Open Course 4.0 | • No of standards developed | • 100 | • Common Methodology to improve knowledge management within the Partnership | • No of Common Methodology to improve knowledge management within the Partnership | • 1 | PC: PC (NEU); ●: «; «: «; «: «; «: «; «: «; ●: «; «: «; «: «; £: «; «: «; «: «; «: «
|  | ● Open Access Course (4 Modules) | • No of Modeuls | • 4 | • Common Toos to indicate real time access opportunities in the Project Area | • No of Common Tools to facilitate real time access opportunities in the Project Area | • 1 | PC: P3 (KJF)
|  | ● Attraction Design Tool | • No of Tools | • 10 | • Common Methodology to improve knowledge management within the Partnership | • No of Common Methodology to improve knowledge management within the Partnership | • 10 | PC: PP6 (ARTIFACTORY)
IO3 | IO3 APPLYING PROJECT-BASED-LEARNING ΤΟ ENGAGE LOCAL STAKEHOLDERS IN TOURISM INNOVATION | • 4 Onsite Lectures and 4 Transnational Training Workshops | • No of Training Events | • 10 | • Individuals with increased capacities developed | • no of Individuals with increased capacities developed | • 36 | PC: ARTIFACTORY PRIME HOLLAND; «: «; «: «; «: ·; «: ·; £: ●; «: ●; «: LAP DELIVERY; «: ·; «: ●
|  | • The TOURiBOOST Local Attraction Plans | • No Plans | • 6 | • Advanced instruments developed to support business innovation at EU Level | • No of Advanced instruments developed to support business innovation at EU Level | • 1 | PC: ALL; «: Standard Plannning Form (by PP6 ARTIFACTORY); «: «; «: «; «: «; ●: «; «: «; «: «; £: «; «: «; «: «; «: ●
|  | • The TOURiBOOST iBook | • No iBooks | • 6 | • Advanced instruments developed to support business innovation at EU Level | • No of Advanced instruments developed to support business innovation at EU Level | • 6 | PC: ALL; «: «; «: «; «: «; ●: «; «: «; «: «; «: ·; «: «; «: ·
[9 empty] | SEPTEMBER (M1) | OCTOBER (M2) | NOVEMBER (M3) | DECEMBER (M4) | JANUARY (M5) | FEBRUARY (M6) | MARCH (M7) | APRIL (M8) | MAY (M9) | JUNE (M10) | JULY (M11) | AUGUST (M12) | SEPTEMBER (M13) | OCTOBER (M14) | NOVEMBER (M15) | DECEMBER (M15) | JANUARY (M17) | FEBRUARY (M18) | MARCH (M19) | APRIL (M20) | MAY (M21) | JUNE (M22) | JULY (M24 | AUGUST (M24)
IO4 | VAILDATING PROFESSIONAL SKILLS TO SUPPORT LOCAL STAKEHOLDERS ACCESS KEY TOURISM MARKETS | ● New EQF Professional Profile (Tourism Planner) | • No of profiles developed | • 1 | • no of innovations in the Project Area | • No of innovations in the Project Area | • 1 | PC: ALL; «: «; «: «; £: «; «: «; «: «; «: «
|  | ● EQF Certification Level (ECTS) | • No of lectures | • 4 | · Creation of individuals with increased capacities in tourism planning | • Creation of individuals with increased awareness in tourism planning | • 18 (3*6) | PC: ALL; ●: «; «: «; «: «; «: «; «: «; «: «
IO5 | SMART SKILLS OBSERVATORY IN HERITAGE TOURISM | • Marketing and Distrubution Strategy | • No of platforms | • 2 | • 1 transnational tool for the education of tourism stakeholders | • No of permanent tools for the education of tourism stakeholders | • 1 | PC: PP3 (KJF); «: «; «: «; «: «
|  | • MOC on Tourism Business Incubator | • No of Docs | • 60 | • 60 stakeholders with increased capacities created | • No of stakeholders with increased capacities created | • 60 (10*6) | PC: PP2 (TÜRSAB); ●: «; «: «; «: «; «: «; «: «; «: «; «: «; ●: «
|  | • Project Area Attraction Map | • No of Maps | • 6 | • Aolicy rrecommendations for tourism innovation developed | • No policy rrecommendations for tourism innovation developed | • 24 | PC: INEUROPA; «: «; «: «; «: «
|  | • iBook | • No of Docs | • 1 | • 60 tourism attractions proactiviley promoted | • no of tourism attractions proactiviley promoted | • 60 (10*6) | PC: STICHTING; «: «; «: «; £: «; «: «; «: «; «: «; ●: «; «: «; «: «; «: ●
MULTIPLIER EVENT | MULTIPLIER EVENT 1 | • MULTIPLIER EVENTS | • No of Local Events | • 1 | • Conference participants attracted | • no of Conference participants attracted | • 30 | PC: PP3 (KJF); ●: ·
| MULTIPLIER EVENT 2 | • MULTIPLIER EVENTS | • No of Local Events | • 2 | • Conference participants attracted | • no of Conference participants attracted | • 30 | PC: PP4 (STICHTING); «: ·
| MULTIPLIER EVENT 3 | • MULTIPLIER EVENTS | • No of Local Events | • 3 | • Conference participants attracted | • no of Conference participants attracted | • 30 | PC: PP5 (INEUROPA); «: ·
| MULTIPLIER EVENT 4 | • MULTIPLIER EVENT IN CHIOS | • No of Local Events | • 4 | • Conference participants attracted | • no of Conference participants attracted | • 30 | PC: PP6 (ARTIFACTORY); «: ·
| MULTIPLIER EVENT 5 | • The Project’s MULTIPLIER EVENTS | • No of International Conferences | • 1 | • Conference participants attracted | • no of Conference participants attracted | • 120 | PC: PP2 (TÜRSAB); «: ·
[9 empty] | SEPTEMBER (M1) | OCTOBER (M2) | NOVEMBER (M3) | DECEMBER (M4) | JANUARY (M5) | FEBRUARY (M6) | MARCH (M7) | APRIL (M8) | MAY (M9) | JUNE (M10) | JULY (M11) | AUGUST (M12) | SEPTEMBER (M13) | OCTOBER (M14) | NOVEMBER (M15) | DECEMBER (M16) | JANUARY (M17) | FEBRUARY (M18) | MARCH (M19) | APRIL (M20) | MAY (M21) | JUNE (M22) | JULY (M24 | AUGUST (M24)
TRAINING ACTIVITIES | ONSITE LECTURE and EVALUATION WORKSHOP 1: | • Onsite Thematic Lecture 1 “UNDERSTANDING THE TRAVEL MOTIVE” | • No of lectures delivered | • 1 | • 1 advanced methodologies for pilot project applications utilized | • No of advanced tools for pilot project applications | • 1 | PC: PC (NEU); «: Konya
|  | • Evaluation Workshop | • No of Evaluation Workshops | • 1 | • Participants with increased capacities developed | • Participants with increased capacities developed | • 36 | PC: PP4 (PRIME HOLLAND)
| ONSITE LECTURE and EVALUATION WORKSHOP 2: | • Onsite Thematic Lecture 1 “UNDERSTANDING TOURISM ACCESSIBILITY” | • No of lectures delivered | • 2 | • 1 advanced methodologies for pilot project applications utilized | • No of advanced tools for pilot project applications | • 1 | PC: PP4 (KJF); «: Budapest
|  | • Evaluation Workshop | • No of Evaluation Workshops | • 6 | • Participants with increased capacities developed | • Participants with increased capacities developed | • 36 | PC: PP4 (PRIME HOLLAND)
| ONSITE LECTURE and EVALUATION WORKSHOP 3: | • Onsite Thematic Lecture 3 “TOURISM PLANNING: FROM RESOURCES TO ATTRACTIONS” | • No of lectures delivered | • 7 | • 1 advanced methodologies for pilot project applications utilized | • No of advanced tools for pilot project applications | • 1 | PC: ALL; «: Modena
|  | • Evaluation Workshop | • No of Evaluation Workshops | • 1 | • Participants with increased capacities developed | • Participants with increased capacities developed | • 36 | PC: PP4 (PRIME HOLLAND)
| ONSITE LECTURE and EVALUATION WORKSHOP 3: | • Onsite Thematic Lecture 4 “TOURISM PLANNING: FROM ATTRACTIONS TO EXPERIENCES” in CHIOS/GR | • No of lectures delivered | • 1 | • 1 advanced methodologies for pilot project applications utilized | • No of advanced tools for pilot project applications | • 1 | PC: PP6 (ARTIFACTORY); «: Istanbul
|  | • Evaluation Workshop | • No of Evaluation Workshops | • 21 | • Participants with increased capacities developed | • Participants with increased capacities developed | • 100 | PC: PP4 (PRIME HOLLAND)
[11 empty] | M3 |  | M7 |  |  |  | M11 |  |  | M14 | [11 empty] | M18
EXPLANATION TABLE
| · | Delivery Month
| ··· | Time frame Box with Multiple Outputs
| « | Preparation Period
| · | Activity Start - End
Note on J6: Author: Grant Agreement Pertnership Agreement signed by the COORDINATOR
Note on M7: Author: Election of the Project Committees
Note on L8: Author: TOURiBOOST TIME TABLE PROJECT MANUAL Templates Archive
Note on T8: Author: PM Toolkit 2nd Update PROJECT MANUAL PM Toolkit 1st Updated
Note on Z8: Author: PM Toolkit 3rd Update PROJECT MANUAL PM Toolkit 1st Updated
Note on L9: Author: QUALITY ASSURANCE PLAN
Note on M12: Author: 1st Coordination Meeting in Konya, Tukjey
Note on R12: Author: 2nd PV Meeting in Budapest, HUngary
Note on V12: Author: 3rd PC Meeting TELECONFERENCE
Note on Y12: Author: 4th PC Meeting in Modena, Italy
Note on AB12: Author: 5th PC Meeting TELECONFERENCE
Note on AE12: Author: 6th PC Meeting in ISTANBUL, TURKEY
Note on N14: Author: Internal Monitoring Report 1
Note on S14: Author: Internal Monitoring Report 2
Note on Z14: Author: Internal Monitoring Report II
Note on AG14: Author: Internal Monitoring Report
Note on N15: Author: Internal Monitoring Report 1
Note on S15: Author: Internal Monitoring Report 2
Note on V15: Author: INTERIM REPORT
Note on Z15: Author: Internal Monitoring Report II
Note on AG15: Author: Internal Monitoring Report
Note on AJ15: Author: FINAL REPORT
Note on L19: Author: Project Website
Note on L20: Author: Social Media Campagin
Note on L22: Author: COMMUNICATION PLAN
Note on M23: Author: 1st Press Conference in Konya, TR
Note on AE23: Author: 2nd PRESS CONFERENCE AT THE MULTIPLIER EVENT ISTANBUL TURKEY
Note on K25: Author: Project Logo and Brochure
Note on M26: Author: Project Brochure -eform
Note on M27: Author: 1st NEWSLETTER
Note on AG27: Author: 6th NEWSLETTER
Note on P31: Author: STAKEHOLDER SURVEY
Note on Q31: Author: STAKEHOLDER SURVEY
Note on S32: Author:
Note on V33: Author: RESEARCH REPORT
Note on Q35: Author: $ MODULES
Note on W35: Author: $ MODULES
Note on M39: Author: 1st Coordination Meeting in Konya, Tukjey
Note on R39: Author: 2nd PV Meeting in Budapest, HUngary
Note on V39: Author: 3rd PC Meeting TELECONFERENCE
Note on Y39: Author: 4th PC Meeting in Modena, Italy
Note on AB39: Author: 5th PC Meeting TELECONFERENCE
Note on AE39: Author: 6th PC Meeting in ISTANBUL, TURKEY
Note on Y40: Author: Delivery Date Attraction Plans
Note on Z52: Author: 1st DISSEMINATION EVENT IN HUNGARY
Note on AA53: Author: 2nd DISSEMINATION EVENT IN HOLLAND
Note on AB54: Author: 3rd DISSEMINATION EVENT IN ITALY
Note on AC55: Author: 4th DISSSEMINATION EVENT IN GREECE
Note on AE56: Author: MULTIPLIER EVENT "SMART TOUROSM OBSERVATORY in Istanbul, Turkey

## DAY SET PER IO
|  | IO1 | IO2 | IO3 | IO4 | IO5
1 | NEU | 60 | 120 | 60 | 140 | 40
2 | TURSAB | 60 | 15 | 50 | 180 | 80
3 | JKF | 60 | 30 | 50 |  | 30
4 | PRIME | 30 | 10 | 70 |  | 20
5 | INEUROPA | 40 | 10 | 60 |  | 20
6 | ARTIFACTORY | 30 | 40 | 40 | 60 | 20

## TASK DISTRIBUTION
TOURiBOOST
CfP 2018/KA2/StrategicPartnerships/HE
Reorienting tourism education with digital, social and intercultural competences to support local stakeholders tackle strategic innovation in tourism
PARTNERS
OUTPUTS | ACTIVITIES |  |  | QUANTIFIED OUTPUTS | Measurement Unit | Target Value | QUANTIFIED RESULTS | Measurement Unit | Target Value | LEAD | NEU | TURSAB | KJF | STICHTING | ARTIFACTORY | INEUROPA
TRANSNATIONAL PROJECT MANAGEMENT, ADMINISTRATION, COORDINATION & MONITORING | 1.1: TRANSNATIONAL PROJECT MANAGEMENT AND ADMINISTRATION | 1 | 1 | • Contractual Procedure | • No of official docs signed (Grant Agreement, Consortium Agreement) | • 2 | • New Transnational Partnership established | • No of Project Partners activated | • 6 | PC (NEU) | ● |  | ● | ● | ● | ●
|  | 2 | 2 | • Steering Group Committee, Technical Committee, Quality Control Committee | • No of Project Committees established (SGC, TC, QCC) | • 3 | • Common Management Structure established | • No of Common Management Structure adopted | • 1 | PC (NEU) | ● | ● | ● | ● | ● | ●
|  | 3 | 3 | • The Project Management Toolkit | • No of common management tools developed | • 4 | • Common Management Standards adopted | • No of Common Management Standards adopted | • 4 | PC (NEU) | ●
|  | 4 | 4 | • The Quality Assurance Plan | • No of common management tools developed | • 5 | • Common Management Standards adopted | • No of Common Management Standards adopted | • 5 | PP3 (KJF) |  |  | ●
|  | 5 | 5 | • Compilation of the Project’s AV and Media Record | • No of docs and media formats compiled | • 300 | • Stakeholders with direct access to the Project Record | • No of Stakeholders with direct access to the Project Record | • 160 (60 SMEs and 100 Stakeholders) | PC (NEU) | ● |  |  |  | ●
| 1.2: TRANSNATIONAL PROJECT COORDINATION | 6 | 6 | • no of project coordination meetings implemented | · no of project coordination meetings implemented | · 4 | · Staff members with increased capacities in the management of EU Projects developed | • No of Staff members with increased capacities in the management of EU Projects developed | • 30(5*6) | PC | ● | ● | ● | ● | ● | ●
| 1.3 TRANSNATIONAL PROJECT MONITORING | 7 | 7 | • Organizational Chart • Project Checklists for the Quality of Project Deliverables • Internal Interim Reports | • Organizational Chart • Project Checklists for the Quality of Project Deliverables • Internal Interim Reports | • 1 • 1 • 4 | • Physical object implemented • Project budget absorbed • Project Completion Statement | • % of the physical object implemented • % of Project Budget absorbed • no of Project Completion Statements | • 95% of the physical project object implemented • 95% of the financial project object implemented • 1 | PC | ● | ● | ● | ● | ● | ●
|  | 8 | 8 | • Interim Report • Final Report | • no of interim reports • no of final reports | • 1 • 1 | • Physical object implemented • Project budget absorbed • Project Completion Statement | • % of the physical object implemented • % of Project Budget absorbed • no of Project Completion Statements | • 95% of the physical project object implemented • 95% of the financial project object implemented • 1 | PC | ● | ● | ● | ● | ● | ●
COMMUNICATION | 2.1 : THE PROJECT’s INTEGRATED COMMUNICATION, DISSEMINATION, VISIBILITY AND TRANSPARENCY SOURCES | 9 | 1 | • The Project’s Integrated Communication, Dissemination and Visibility Platform | • no of highly advanced ICT tools utilized | • 2 (website and Moodle Platform) | • Permanent Information and Transparency Sources for Project Activities | • No of Permanent Information and Transparency Sources for Project Activities | • 2 | PC (NEU) | ●
|  | 10 | 2 | • The TOURiBOOSTER Social Media Campaign | • no of social media tools utilized | • 4 (Instagram, Pinterest, Facebook Metrics, Twitter) | • Development of social media communities for the DIVERTIMENTO heritage game | • No of social media communities involved in the heritage game | • 14 (2*7) | PP2 (TÜRSAB) |  |  |  | ●
| 2.2. PROJECT-DRIVEN COMMUNICATION STRATEGY FOR SELECTED TARGET PUBLICS FROM THE PUBLIC, PRIVATE AND THIRD SECTOR AT EU AND INTERNATIONAL LEVEL | 11 | 3 | • The Common Visibility, Communication and Dissemination Plan (CDV Plan) PC | • No of CDV Plans developed | • 1 | • Innovative communication concept implemented | • no of innovative communication concepts implemented | • 1 | PP6 (ARTIFACTORY) |  |  |  |  | ●
|  | 12 | 4 | • Press Conferences | • No of Press Conferences | • 2 (Kick Off Meeting & Multiplier Event) | • Press articles published about Project activities in the Cooperation Area | • no of press articles published about Project activities in the Cooperation Area | 8 | PC (NEU) & PP2 (TÜRSAB) | ● | ●
| 2.3 DISSEMINATION OF PROJECT OUTPUTS & PROJECT BRANDING AT INTERNATIONAL LEVEL | 13 | 5 | • The TOURiBOOSTER Visual Identity Kit (Project Logo; Stand with Banner; Mousepad Calendar; Pen; Cotton Bag ) | • No of brochures | • 1 | • Tourism stakeholders directly reached in the project area | • No of tourism stakeholders directly reached in the Cooperation Area | • 140 (20*7) | PC (NEU) |  |  |  |  | ●
|  | 14 | 6 | • Project Brochure | • No of visual identity tools produced | • 15 | • Joint Outreach Tools to reach directly Tourism stakeholders in the project area | • No of Joint Outreach Tools to reach directly Tourism stakeholders in the project area | • 1 | PC (NEU) |  |  |  |  | ●
|  | 15 | 7 | • 6 Project Newsletters | • No of Newsletters |  | • Joint Outreach Tools to reach directly Tourism stakeholders in the project area | • No of Joint Outreach Tools to reach directly Tourism stakeholders in the project area | • 6 | PP2 (TÜRSAB) | ● | ● | ● | ● | ● | ●
|  | 16 | 8 | • The TOURIBBOSTER Promotional Spot | • No of AV productions implemented | • 1 | • Heritage tourism products proactively promoted | • No of heritage products proactively promoted | • 7 | PP2 (TÜRSAB) | [5 empty] | ●
IO1 | IDENTIFICATION OF SKILLS NEEDS AND EMERGING SKILLS TO ASSIST CAPACITY BUILDING OF TOURISM STAKEHOLDERS | 17 | 1 | • Joint CB Survey Study to Investigate Entrepreneurial/Stakeholders Needs and Skill Needs of Human Capital in the Project Area | • No of joint surveys conducted | • 1 | • Recommendations for the skills updates | • No of recommendations for the skills updates | • 12 | P3 (KJF) | ● | ● | ● | ● | ● | ●
|  | 18 | 2 | • Stakeholder Training Workshops to identify a new generation of experience-based tourism products in the territory | • No of Stakeholder Workshops | • 1 | • New products and services detected | • No of new products and services detected | • 1 | ALL | ●
|  | 19 | 3 | • Research Report | • No of Research Reports | • 1 | • New business models detected | • No of new business models detected | • 6 | ALL |  |  | ●
IO2 | LINKING STAKEHOLDER EDUCATION TO KEY TOURISM EXPERIENCES AND QUALITY SERVICES IN THE TERRITORY | 20 | 1 | ● Massive Online Open Course 4.0 | • No of standards developed | • 100 | • Common Methodology to improve knowledge management within the Partnership | • No of Common Methodology to improve knowledge management within the Partnership | • 1 | PC (NEU) | ●
|  | 21 | 2 | ● Open Access Course (4 Modules) | • No of Modeuls | • 4 | • Common Toos to indicate real time access opportunities in the Project Area | • No of Common Tools to facilitate real time access opportunities in the Project Area | • 1 | P3 (KJF) | [5 empty] | ●
|  | 22 | 3 | ● Attraction Design Tool | • No of Tools | • 10 | • Common Methodology to improve knowledge management within the Partnership | • No of Common Methodology to improve knowledge management within the Partnership | • 10 | PP6 (ARTIFACTORY) | [5 empty] | ●
IO3 | IO3 APPLYING PROJECT-BASED-LEARNING ΤΟ ENGAGE LOCAL STAKEHOLDERS IN TOURISM INNOVATION | 23 | 1 | • 4 Onsite Lectures and 6 Transnational Training Workshops | • No of Training Events | • 10 | • Individuals with increased capacities developed | • no of Individuals with increased capacities developed | • 36 | ARTIFACTORY PRIME HOLLAND |  |  |  | ● |  | ●
|  | 24 | 2 | • The TOURiBOOSTER Local Attraction Plans | • No Plans | • 6 | • Advanced instruments developed to support business innovation at EU Level | • No of Advanced instruments developed to support business innovation at EU Level | • 1 | ALL | ● | ● | ● | ● | ● | ●
|  | 25 | 3 | • The TOURiBOOSTER iBook | • No iBooks | • 6 | • Advanced instruments developed to support business innovation at EU Level | • No of Advanced instruments developed to support business innovation at EU Level | • 6 | ALL | ● | ● | ● | ● | ● | ●
IO4 | VAILDATING PROFESSIONAL SKILLS TO SUPPORT LOCAL STAKEHOLDERS ACCESS KEY TOURISM MARKETS | 26 | 1 | ● New EQF Professional Profile (Tourism Planner) | • No of profiles developed | • 1 | • no of innovations in the Project Area | • No of innovations in the Project Area | • 1 | ALL | ●
|  | 27 | 2 | ● EQF Certification Level (ECTS) | • No of lectures | • 4 | · Creation of individuals with increased capacities in tourism planning | • Creation of individuals with increased awareness in tourism planning | • 18 (3*6) | ALL |  |  | ● |  |  | ●
IO5 | TOURISM BUSINESS INCUBATOR | 28 | 1 | • Marketing and Distrubution Strategy | • No of platforms | • 2 | • 1 transnational tool for the education of tourism stakeholders | • No of permanent tools for the education of tourism stakeholders | • 1 | PP3 (KJF) |  |  | ●
|  | 29 | 2 | • SMART SKILLS OBSERVATORY | • No of Docs | • 60 | • 60 stakeholders with increased capacities created | • No of stakeholders with increased capacities created | • 60 (10*6) | PP2 (TÜRSAB) | ●
|  | 30 | 3 | • Project Area Attraction Cluster | • No of Maps | • 6 | • Aolicy rrecommendations for tourism innovation developed | • No policy rrecommendations for tourism innovation developed | • 24 | INEUROPA | ● | ● | ● | ● | ● | ●
|  | 31 | 4 | • iBook | • No of Docs | • 1 | • 60 tourism attractions proactiviley promoted | • no of tourism attractions proactiviley promoted | • 60 (10*6) | ARTIFACTORY | ● | ● | ● | ● | ● | ●
MULTIPLIER EVENTS | MULTIPLIER EVENT 1 | 32 | 1 | • MULTIPLIER EVENTS | • No of Local Events | • 1 | • Conference participants attracted | • no of Conference participants attracted | • 30 | PP3 (KJF) |  | ●
| MULTIPLIER EVENT 2 | 33 | 2 | • MULTIPLIER EVENTS | • No of Local Events | • 2 | • Conference participants attracted | • no of Conference participants attracted | • 30 | PP4 (STICHTING)
| MULTIPLIER EVENT 3 | 34 | 3 | • MULTIPLIER EVENTS | • No of Local Events | • 3 | • Conference participants attracted | • no of Conference participants attracted | • 30 | PP5 (INEUROPA) |  |  | ●
| MULTIPLIER EVENT 4 | 35 | 4 | • MULTIPLIER EVENTS | • No of Local Events | • 4 | • Conference participants attracted | • no of Conference participants attracted | • 30 | PP6 (ARTIFACTORY) |  |  |  | ●
| MULTIPLIER EVENT 5 | 36 | 5 | • MULTIPLIER EVENTS | • No of International Conferences | • 1 | • Conference participants attracted | • no of Conference participants attracted | • 120 | PP2 (TÜRSAB) |  |  |  |  | ● | ●
|  | 36 | [8 empty] | 19 | 12 | 16 | 14 | 16 | 17
TRAINING ACTIVITIES | TRAINING EVENT 1 |  |  | • Onsite Thematic Lecture 1 “UNDERSTANDING THE TRAVEL MOTIVE” | • No of lectures delivered | • 1 | • 1 advanced methodologies for pilot project applications utilized | • No of advanced tools for pilot project applications | • 1 | PC (NEU)
|  |  |  | • Evaluation Workshop | • No of Evaluation Workshops | • 1 | • Participants with increased capacities developed | • Participants with increased capacities developed | • 36 | PP4 (PRIME HOLLAND)
| TRAINING EVENT 2 |  |  | • Onsite Thematic Lecture 1 “UNDERSTANDING TOURISM ACCESSIBILITY” | • No of lectures delivered | • 2 | • 1 advanced methodologies for pilot project applications utilized | • No of advanced tools for pilot project applications | • 1 | PP4 (KJF)
|  |  |  | • Evaluation Workshop | • No of Evaluation Workshops | • 6 | • Participants with increased capacities developed | • Participants with increased capacities developed | • 36 | PP4 (PRIME HOLLAND)
| TRAINING EVENT 3 |  |  | • Onsite Thematic Lecture 3 “TOURISM PLANNING: FROM RESOURCES TO ATTRACTIONS” | • No of lectures delivered | • 7 | • 1 advanced methodologies for pilot project applications utilized | • No of advanced tools for pilot project applications | • 1 | ALL
|  |  |  | • Evaluation Workshop | • No of Evaluation Workshops | • 1 | • Participants with increased capacities developed | • Participants with increased capacities developed | • 36 | PP4 (PRIME HOLLAND)
| TRAINING EVENT 4 |  |  | • Onsite Thematic Lecture 4 “TOURISM PLANNING: FROM ATTRACTIONS TO EXPERIENCES” | • No of lectures delivered | • 1 | • 1 advanced methodologies for pilot project applications utilized | • No of advanced tools for pilot project applications | • 1 | PP6 (ARTIFACTORY)
|  |  |  | • Evaluation Workshop | • No of Evaluation Workshops | • 21 | • Participants with increased capacities developed | • Participants with increased capacities developed | • 100 | PP4 (PRIME HOLLAND)
[13 empty] | M3 |  | M7
EXPLANATION TABLE
| · |  |  | Delivery Month
| ··· |  |  | Time frame Box with Multiple Outputs
| « |  |  | Preparation Period
| · |  |  | Activity Start - End

## Sheet1
ARTIFACTORY
IO1 | 4110
IO2 | 5480
IO3 | 5480
IO4 | 8220
IO5 | 1370
EVENTS | 3000
TRAVEL | 3450
MGMT | 7000